## EARTH CALCULATION
Earth Calculation for Protective work along the Right Bank of Boleswar River from km 22.200 to km 25.300 ; Total = 3.100 km Gabtola to Bogi under Polder No. 35/1, Upazila - Morrelganj, District- Bagerhat under Bagerhat O&M Division, BWDB, Bagerhat.
| Pre work | [5 empty] | Post work
10 | 2.55 | [5 empty] | 10 | 2.55
12 | 1.57 | 2.06 | 2 | 4.12 |  |  | 24 | -0.5 | 1.025 | 14 | 14.35
14 | 1.26 | 1.415 | 2 | 2.83
17 | 1.11 | 1.185 | 3 | 3.555
20 | 0.82 | 0.965 | 3 | 2.895 | [5 empty] | 14 | 14.35
22 | 0.5 | 0.66 | 2 | 1.32
24 | 0.11 | 0.685 | 10 | 6.85
|  |  | 22 | 21.57 |  |  | N/A = | 7.22 | Sqm
| Vol = |  | 1000 | x | 7.22 |  |  | = | 7220 | cum
Toe portion
|  |  | 1000 | x | 1.56 | x | 1 | = | 1560 | cum
[9 empty] | 8780 | cum
Synthetic bag/Ganny bag
| Pre work | [5 empty] | Post work
18 | 1.58 | [5 empty] | 18 | 1.58
20 | 1.15 | 1.365 | 2 | 2.73 |  |  | 44.7 | -0.5 | 0.54 | 26.7 | 14.418
22 | -2.36 | -0.605 | 2 | -1.21
24 | -4.26 | -3.31 | 2 | -6.62
26 | -6.16 | -5.21 | 2 | -10.42 | [5 empty] | 26.7 | 14.418
28 | -8.06 | -7.11 | 2 | -14.22
30 | -9.65 | -8.855 | 2 | -17.71
32 | -11.36 | -10.505 | 2 | -21.01
33.5 | -12.36 | -11.86 | 1.5 | -17.79
35.4 | -14.36 | -13.36 | 1.9 | -25.384
36.8 | -14.95 | -14.655 | 1.4 | -20.517
38.8 | -15.09 | -15.02 | 2 | -30.04
40.7 | -15.26 | -15.175 | 1.9 | -28.8325
42.7 | -15.78 | -15.52 | 2 | -31.04
44.7 | -18.5 | -17.14 | 2 | -34.28
|  |  | 26.7 | -256.3435 |  |  | N/A = | 270.7615 | Sqm
| Vol = |  | 800 | x | 270.7615 |  |  | = | 216609.2 | cum
|  |  |  | 0.04 | cum per bag
|  |  | No of bag | [5 empty] | 5415230 | Nos
| Pre work | [5 empty] | Post work
0 | 2 | [5 empty] | 0 | 2
0.6 | 1.5 | 1.75 | 0.6 | 1.05 |  |  | 3 | 4 | 3 | 3 | 9
1.2 | 1.4 | 1.45 | 0.6 | 0.87 |  |  | 7 | 4 | 4 | 4 | 16
15 | 0 | 0.7 | 13.8 | 9.66 |  |  | 15 | 0 | 2 | 8 | 16
|  |  | 15 | 11.58 | [5 empty] | 15 | 41
[7 empty] | N/A = | 29.42 | Sqm
| Vol | = | 1000 | 29.42 |  |  |  | = | 29420 | cum
(S.M. Ahsan Habib)
Sub- Divisional Engineer (A.C)
Satkhira O&M Sub-Division-1
BWDB, Satkhira
(Muhammad Abu Hanif)
Sub-Asstt. Engineer
Parulia O&M Section
BWDB, Satkhira.
(B. M. Abdul Momin) Executive Engineer (C.C)
Satkhira O&M Division-1
BWDB, Satkhira
(Muhammad Abu Hanif)
Sub-Asstt. Engineer /SO
Jhalodangha O&M Section
BWDB,Bagerhat.
(Faruk Ahmed)
Sub- Divisional Engineer
Bagerhat O&M Sub-Division
BWDB,Bagerhat.

## ABSTRACT
Abstract cost of Protective work along the Right Bank of Panguchi River from km 0.000 to km 1.000 ; Total = 1000m at Fulhata Bazar & from km 2.100 to km 3.600 ; Total = 1500m at Sinnikhali , Upazila - Morrelganj, District- Bagerhat under Bagerhat O&M Division, BWDB, Bagerhat.
Sl. No. Code no. | Item Descriptions | Quantity | Unit | Rate (Tk.) | Amount (Tk.)
1 | 2 | 3 | 4 | 5 | 6
1 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge. | 206400 | sqm | 38.13 | 7870032
2 16-100 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge. | 52 | Nos | 367.41 | 19105.32
3 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cmx75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charge. | 4 | Nos | 1421.49 | 5685.96
4 40-230 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2:4 with cement, sand (FM>=2.0) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 18 N/mm² including grading, washing stone chips, mixing, laying in forms, onsolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. omplete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge.
A) 40-230-25 | Block Size: 45cmx45cmx45cm. | 277621 | Each | 1442.18 | 400379453.78
B) 40-230-45 | Block Size: 35cmx35cmx35cm. | 364501 | Each | 650.79 | 237213605.79
C) 40-230-40 | Block Size: 40cmx40cmx20cm. | 144452 | Each | 499.32 | 72127772.64
5 40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.
A) 40-270-10 | Within 200 m. | 1943.6142 | Cum | 1395.03 | 2711400.1174
B) 40-270-20 | 200 m to 500 m. | 4535.0998 | Cum | 2185.1 | 9909646.573
6 40-290 | Dumping work of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks over a uniform area from properly positioned by engine boat upto an accuracy of 10cm monitoring with Total Station. The dumping area to be determined by conducting bathymetric survey, furnishing topographic site plan, cross section, dumping alignment, providing location of benchmark and stake at batches of dumping activity, doing by a river survey team ( including survey manager, hydrographic surveyor, Auto cad operator, etc.) with total station. Sequential stacking of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks on the engine boat, carrying the Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks to dumping area and dumping the block from the boat by manual labour or any other means, all materials & charges etc. complete as per direction of engineer in charge, specification and design.
A) 40-290-10 | Within 200 m. | 11720.9832 | Cum | 1905.43 | 22333513.0188
B) 40-290-20 | 200 m to 500 m. | 27348.9608 | Cum | 2466.67 | 67460861.1365
7 40-320 | Supplying of geo-textile bags (empty) of different sizes and capacity at project/work site, making the bag with standard Geo-Textile fabric (100% Polypropylene Fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordance with the detailed drawing and Technical Specifications included in the Tender Document and Schedule of Rates of BWDB, protecting the geo-textile bags form UV ray or any other damages including cost of all materials, labours, incidental charges etc. complete as per direction of Engineer in charge.
40-320-15 | Geo-bag; inner size:1100mmx850mm, outer size:1150mmx900mm, geo-fabric th.=>3.0mm, Fill Vol: 0.1333cum; wt: 200kg | 410347 | Each | 299.03 | 122706063.41
8 40-330 | "[Dumping with Barge & Total Station] Filling and dumping of geo-textile bags of different sizes and capacity at project/work site, protecting from UV ray or any other damages, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking with synthetic enamel paint during counting, dumping from properly positioned and anchored flat top barge/pontoon over an area as per drawing, maintaining & recording the dumping position of the barge/pontoon uning total station including loading, unloading, sequential piling of geo-bags on the dumping edge of barge/pontoon, cost of all materials & equipments and its mobilization, labour, incidental charges, etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]"
40-330-15 | Geo-bag; inner size:1100mmx850mm, outer size:1150mmx900mm,, Fill Vol: 0.1333cum; wt: 200kg | 410347 | Each | 206.37 | 84683310.39
9 40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge.
40-550-30 | FM : 1.0 to 1.5 | 2658.0217 | Cum | 1316.45 | 3499152.6839
10 40-520 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge:
A)40-520-20 | Well graded between 40mm to 20mm size. | 2928.6109 | Cum | 4564.59 | 13367907.8292
B)40-520-30 | Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used) | 2928.6109 | Cum | 5028.49 | 14726490.4055
11 40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² ssure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextilematerial from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric).
40-500-40 | Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N. | 37991.9213 | sqm | 250.13 | 9502919.2707
12 40-920 | Earth work in cutting and filling of eroded bank of river, channel etc. to design slope, including levelling, dressing and compacting the earth in 150mm layers and preparation of the base for bank protection work and use the excess material for filling the ditches on the bank within 50 m or specified in the drawing, if no ditches to be filled then excess material shall be disposed of at least 100 m from the bank line on C/S etc. complete as per direction of Engineer in charge. | 9060 | Cum | 218.36 | 1978341.6
13 16-130 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/ road/ compound etc. manually compacted by 7.0 kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceeding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge.
A)16-130-10 | 0 m to 3 m height. | 71000 | Cum | 262.03 | 18604130
14 16-720 | Filling ditch/pond/channel/khal etc or land development/improvment by dredged earth from river bed (all kind of soil but excluding organic material) , carried by Bulkhead/cargo/ boat or any other mean, loading and unloading/ Disposing/placing the dredged materials in the designated area upto 1 km from river bank by bulkhead dredger including , maintaining slopes, levelling and dressing in layers upto finished level with all lifts & leads etc. all complete as per direction of the Engineer in charge.
A)16-720-10 | Bulkhead/cargo/boat or any other means: within 1 km along the river | 40037.8 | Cum | 141.27 | 5656140.006
15 4-700 | Erection and maintenance of site office and removal of the same after completion of work as per approved plans & drawings for the use of the Engineer-in-charge & his staff, Task force and field laboratory with adequate foundation, brick walls, acceptable outside & inside wall surface, concrete floor with floor tiles, false ceiling of gypsum board, windows are to be glazed & provided with steel grill & screen/blinds, doors with approved locks, furniture & fittings of approved quality, equipment & plant of approved quality, electricity, running water, sewerage, security fencing, 5 KVA stand-bye generator, IBM compatible PC with monitor, uninterruptible power supply (UPS), LaserJet printer (minimum 25 ppm), first aid-box, safety helmet, level/theodolite/EDM, consumables, stationeries, day & night guards & a tea boy and site office shall be ready for occupation by the Engineer-in-charge within 28 days of commencement of work, etc. complete as per direction of Engineer-in-charge. (This is a time related item; proportionate payment for this item shall be made distributing in each bill on the basis of percentage progress of the whole works under contract)
4-700-10 | Site office of minimum 38 sqm plinth area. | 5 | Nos | 508581.43 | 2542907.15
16 04-710 | Temporary lease of land for 1 (one) year with necessary compensation for crops or this installation on land for site office, material yard, casting yard, staking yard etc. complete as per direction of Engineer in charge | 500000 | sqm | 33.94 | 16970000
17 10-140 | River Morphological Data Collection/ Bathymetric Survey and river bank topography survey for river/ khal section (section width 251 m to 350 m), including cost of all necessary equipments (Level Machine, Hand GPS, DGPS etc), Necessary personnels (River Morphology Expert for data cosistency checking, Engineer/ Survey Specialist for data processing with survey software and Prepare necessary Table, Graph and Morphologhical parameters calculations, Surveyor & Unskilled Labour for field data collection), Accomodation, Transportation from Headquarter to Site and Site movement and Shaded for Bathymetric Survey for field survey team including necessary fuels and lubricant, Other necessary auxiliary items such as survey flags, pegs with provision of submission of report in hard binded copies (at least 6 copies required), soft copies and raw survet data with provision of 10% random re-survey for data consistency checking as per direcion of Engineer in charge.
10-140-40 | 61 m to 100m | 25 | Nos | 1871.35 | 46783.75
18 Market Rate | Pre work, post work and ongoing work Photograp and video of the project work including aerial video and editing. | 25 | Nos | 2760 | 69000
19 28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements and formworks etc. complete and as per direction of Engineer in charge.
28-200-10 | With stone chips. | 88.5676 | cum | 14932.16 | 1322505.574
20 76-110 | M.S. Work for reinforcement with deformed M.S. bar, fy=300 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge.
76-110-10 | 8mm dia to 30mm dia. | 5928.028 | Kg | 90.32 | 535419.489
21 36-300 | Form work for centering and water tight shuttering as per drawing with wooden planks of different thickness including supply of polythene sheet (1 kg covering 6.5 sqm ) for making shuttering leakproof for all sorts of R.C.C. works in building construction including fitting, fixing by nails, tie rods, nuts and bolts to desired shape and size including levelling and removing the forms etc. after specified period including the cost of all materials as per direction of Engineer in charge.
36-300-10 | Individual and continuous footing of column, raft etc. with 25mm thick wooden planks. | 368.99 | sqm | 695.99 | 256813.3501
22 40-460 | [Geo-textile bag filled with sand cement mixture] Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordance with the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand-cement mixed (6:1 Proportion, sand: F.M ≥ 1.00, Portland cement) , sewing along one transverse (top) side after filling, staking in surable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical pecification, approved design and direction of Engineer in charge.
40-460-10 | Geo-bag; inner size:950mmx750mm, outer size:1000mmx800mm geo-fabric th.=>3.0mm, Fill Vol: 0.0840cum; wt: 125kg | 30960 | Nos | 658.06 | 20373537.6
23 16-500 | Earth work in excavation of foundation trenches in all kinds of soils including levelling, dressing, placing, removal of spoils to a safedistance with initial lead of 30m and lift of 1.5m as per direction of Engineer in charge. | 3088.75 | Cum | 238.12 | 735493.15
24 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials,excluding the cost of formworks etc. complete as per direction of Engineer in charge.
28-120-20 | With 25mm down graded stone chips. | 38.7 | cum | 13107.46 | 507258.702
Total= |  |  |  |  | 1138115250.6962
;
Abstract cost of Estimate for Emergency temporary protective work at left bank of Mongla - Ghasiakhali Channel from km 0.600 to km 0.700 = 100m to protect Rampal Upazila Council and adjacent area in Upazila Rampal, Dist. Bagerhat under NDR Budget under Bagerhat O&M Division, BWDB, Bagerhat, during the year 2019-2020.
Sl. No. Code no. | Item Descriptions | Quantity | Unit | Rate (Tk.) | Amount (Tk.)
1 | 2 | 3 | 4 | 5 | 6
1 40-680 40-680-20 | Supplying, sizing and placing in position local hard wood bullah such as Sonali gul, Tetul, Jam etc. including all taxes and incidental charges (bullah measured at 1/3rd. length from thick end excluding the bark) etc. complete as per direction of Engineer in charge. 40-680-20:Above 13 cm to 15 cm | 669 | m | 315.14 | 210828.66
2 40-690 40-690-20 | Labour charge for driving local hard bullah such as Sonali gul, Tetul, Jam etc. bullah piles on dry land, by monkey hammer etc. complete including charges for all quipments as per direction of Engineer in charge. 40-690-20:Above 13 cm to 15 cm | 456.5 | m | 183.57 | 83799.705
3 40-720 40-720-10 | Supplying, sizing and placing of barrack bamboo pins and stays of diameter >= 8.0 cm in position etc. complete as per direction of Engineer in charge. 40-720-10 :Length: >= 4.5 m to <= 6.0 m. | 334 | Each | 317.06 | 105898.04
4 40-730 40-730-10 | Labour charge for driving barrack bamboo pins of diameter >= 8.0 cm, by hammer or monkey hammer, as per direction of Engineer in charge. 40-730-10:.>= 1.50 m to <= 2.0 m drive, on dry land. | 668 | m | 185.58 | 123967.44
5 40-710 | Supplying, fitting and fixing of half sawn local hard wood walling pieces, fitted with 20mm. dia bolts and nuts at 1.0m c/c etc. complete as per directoin of Engineer in charge: 40-710-10: 15 cm to 18 cm dia | 200.6 | M | 228.65 | 45867.19
6 40-650 40-650-30 | [For Emergency Work] Supplying and filling empty gunny/synthetic bags as approved in design & drawing with sand/ earth available at site sewing the end with sutly, including carrying and placing in position within the site with supply of all materials as per direction of Engineer in charge. 40-650-30: Capacity : 50 kg (Synthetic bag) | 10833 | Each | 37.09 | 401795.97
7 76-115 76-115-20 | M.S Work for reinforcement with Standard deformed bar fy=300 N/mm^2 in RCC works including local handling, cutting, forging,bending,cleaning and fabrication with supply of deformed M.S. bar in different sizes and bending with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge. 76-115-20: 8mm dia to 30mm dia | 143.22 | Kg | 85.47 | 12241.0134
8 16-110 16-110-10 | Earth work by manual labour in constructing/ resectioning of embankment/ canal bank/ road etc. with clayey soil(minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m, and all lifts including throwing the spoils to profiles in layers not exceeding 150mm in thickness, clod breaking upto a maximum size of 100mm, benching the side slopes, stripping/ ploughing the base of embankment and borrow pit area, dug bailing, cutting trees upto 200mm girth, with uprooting stumps, clearing jungles, bailing out water, rough dressing and 150mm cambering at the centre of the crest etc. complete as per specification and direction of Engineer in charge. 16-110-10 : 0 to 3 m height. | 550 | cum | 214.38 | 117909
Total= |  |  |  |  | 1102307.0184
(Faruk Ahmed)
Sub- Divisional Engineer
Bagerhat O&M Sub-Division
BWDB,Bagerhat.
(Muhammad Abu Hanif)
Sub-Asstt. Engineer /S O
Jhalodangha O&M Section
BWDB,Bagerhat.
(Nahid-Uz-Zaman Khan)
Executive Engineer
Bagerhat O&M Division
BWDB, Bagerhat.
(Md. Mosharaf Hossain)
Sub-Assistant Engineer
Sannashi O&M Section
BWDB, Rayenda, Bagerhat.
(Md. Arif Hossen)
Sub-Divisional Engineer(A.C)
Rayenda O&M Sub-Division
BWDB, Rayenda, Bagerhat.

## DETAILED
Detailed Estimate for Protective work along the Right Bank of Panguchi River from km 0.000 to km 1.000 ; Total = 1000m at Fulhata Bazar & from km 2.600 to km 4.100 ; Total = 1500m at Sinnikhali , Upazila - Morrelganj, District- Bagerhat under Bagerhat O&M Division, BWDB, Bagerhat.
Sl. No. | Description | Measurement | [6 empty] | Quantity
1 | 2 | 3 | [6 empty] | 4
1/ 04-180 | Site preparation by manually removing all miscellaneous objectional materials from entire site and removing soil upto 15cm depth including uprooting stumps, jungle clearing, levelling dressing etc. complete as per direction of Engineer in charge.
Area =
|  | 2580 | x | 80 |  | = | 206400 | sqm | 206400 | sqm
2/ 04-180 | Erection of bamboo profile with full bamboo posts and pegs not less than 60mm in diameter and coir strings etc. complete as per direction of Engineer in charge.
|  | No of profile = |  |  |  |  | 52 | Nos | 52 | Nos
3/ 04-120 | Construction of B.M. Pillars at site with first class bricks in cement mortar (1:4) of size 38cmx38cmx75cm on cement concrete (1:2:4) base of size 50cmx50cmx7.5cm with 12mm thick cement plastering (1:2) on exposed surfaces of pillar and cement mortar on top (1:2), with inscription of "BWDB" with 25cm of the pillar below ground level etc. complete including ramming the backfill and the cost of all materials as per direction of Engineer in charg
|  | No of BM Piller |  |  |  |  | 4 | Nos | 4 | Nos
4/ 40-230 | Manufacturing and supplying C.C. blocks in leanest mix. 1:2:4 with cement, sand (FM>=2.0) and Stone Chips (40mm down graded) to attain a 28 days cylinder strength of 18 N/mm² including grading, washing stone chips, mixing, laying in forms, onsolidation, curing for at least 21 days, including preparation of platform, shuttering and stacking in measurable stacks etc. omplete including supply of all materials (steel shutter to be used) as per direction of Engineer in charge.
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
A) 40-230-25 | Block Size: 45cmx45cmx45cm.
|  | 15.5 |  | per cum |  |  |  |  | Stock pile 0.5 cum
|  | 1000 | x | 15.5 |  | = | 15500 | cum
|  | 60 % of |  |  |  | = | 9300 | cum
|  | Per block volume = |  |  |  |  | 0.091125 | cum
|  | No of block = |  |  |  |  | 102057.6132 | Nos | 102058 | nos
3 nos Khal
|  | 4 |  | per cum
|  | 60 | x | 4 |  | = | 240 | cum
|  | 60 % of |  |  |  | = | 144 | cum
|  | Per block volume = |  |  |  |  | 0.091125 | cum
|  | No of block = |  |  |  |  | 1580.2469 | Nos | 1580 | nos
Chainage km 0.500 to km 1.00
|  | Area | = | 500 | 6 | = | 3000 | sqm
|  | No of block = |  |  |  | = | 14814.8148 | nos | 14815 | nos
Slope key 2 portion
|  | 5 | x | 500/0.45 |  | = | 5555.5556 | nos | 5555 | nos
|  | Total no. of block |  |  |  | = | 124008.2305
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | 15.5 |  | per cum |  |  | Stock pile 0.5 cum
|  | 1500 | x | 15.5 |  | = | 23250 | cum
|  | 60 % of |  |  |  | = | 13950 | cum
|  | Per block volume = |  |  |  |  | 0.091125 | cum
|  | No of block = |  |  |  |  | 153086.4198 | Nos | 153086 | nos
Khal
|  | 4 |  | per cum
|  | 20 | x | 4 |  | = | 80 | cum
|  | 60 % of |  |  |  | = | 48 | cum
|  | Per block volume = |  |  |  |  | 0.091125 | cum
|  | No of block = |  |  |  |  | 526.749 | Nos | 527 | nos
|  |  |  | Total |  |  | 153613.1687
|  |  |  | Total |  |  | 277621 | Nos | 277621 | Nos
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
B) 40-230-45 | Block Size: 35cmx35cmx35cm. | 15.5 |  | per cum |  |  |  |  | Stock pile 0.5 cum
|  | 1000 | x | 15.5 |  | = | 15500 | cum
|  | 40 % of |  |  |  | = | 6200 | cum
|  | Per block volume = |  |  |  |  | 0.042875 | cum
|  | No of block = |  |  |  |  | 144606.414 | Nos | 144607 | nos
Khal
|  | 4 |  | per cum
|  | 60 | x | 4 |  | = | 240 | cum
|  | 40 % of |  |  |  | = | 96 | cum
|  | Per block volume = |  |  |  |  | 0.042875 | cum
|  | No of block = |  |  |  |  | 2239.0671 | Nos | 2239 | nos
|  | Total= |  |  |  |  | 146845.481
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | 15.5 |  | per cum
|  | 1500 | x | 15.5 |  | = | 23250 | cum
|  | 40 % of |  |  |  | = | 9300 | cum
|  | Per block volume = |  |  |  |  | 0.042875 | cum
|  | No of block = |  |  |  |  | 216909.621 | Nos | 216909 | nos
Khal
|  | 4 |  | per cum
|  | 20 | x | 4 |  | = | 80 | cum
|  | 40 % of |  |  |  | = | 32 | cum
|  | Per block volume = |  |  |  |  | 0.042875 | cum
|  | No of block = |  |  |  |  | 746.3557 | Nos | 746 | nos
|  |  |  | Total |  |  | 217655.9767
|  |  |  | Total no. block |  |  | 364501 |  | 364501 | nos
C) 40-230-40 | Block Size: 40cmx40cmx20cm. | Ch. 0.00 to Ch.1.00 at Fulhata Bazar
Chainage km 0.00 to chainage km 0.500
|  | Slope = |  | 5.5902 | m
|  | Top width = |  | 1.2 | m
|  |  |  | 6.7902 | m
Area =
|  | 540 | x | 6.7902 |  | = | 3666.6918 | sqm
|  | Surface Area of a block |  |  |  | = | 0.16 | sqm
|  | No of block = |  |  |  |  | 22916.8236 | Nos | 22917 | nos
Chainage km. 0.500 to km 1.000
|  | Slope | = | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Area =
|  | 520 | x | 9.0262 |  | = | 4693.6437 | sqm
|  | Surface Area of a block |  |  |  | = | 0.16 | sqm
|  | No of block = |  |  |  |  | 29335.2732 | Nos | 29335 | nos
Edging block
|  | 1060 | ÷ | 0.4 |  | = | 2650 | nos | 2650 | nos
|  | Total No of block = |  |  |  |  | 54902.0968 | Nos
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | Slope |  | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Area =
|  | 1520 | x | 9.0262 |  | = | 13719.8816 | sqm
|  | Surface Area of a block |  |  |  | = | 0.16 | sqm
|  | No of block = |  |  |  |  | 85749.2603 | Nos | 85750 | nos
Edging block
|  | 1520 | ÷ | 0.4 |  | = | 3800 | nos | 3800 | nos
|  | Total No of block = |  |  |  |  | 89549.2603
|  |  |  | Total |  |  | 144452 |  | 144452 | nos
5/ 40-270 | Labour charge for protective works in laying CC blocks of different sizes including preparation of base, watering and ramming of base etc. complete as per direction of Engineer in charge.
A) 40-270-10 | Within 200 m.
Volume =
|  | 40x40x20 |  | 144452 |  | x | 0.032 | = | 4622.464 | Cum
|  | 45x45x45 |  | 20370.3704 |  | x | 0.091125 | = | 1856.25
[9 empty] | 6478.714 | Cum
|  | 30% of = |  |  | = |  | 1943.6142 | Cum | 1943.6142 | Cum
B) 40-270-20 | 200 m to 500 m. | 70% of = |  |  |  |  | 4535.0998 | Cum
[8 empty] | = | 4535.0998 | Cum
6/ 40-290 | Dumping work of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks over a uniform area from properly positioned by engine boat upto an accuracy of 10cm monitoring with Total Station. The dumping area to be determined by conducting bathymetric survey, furnishing topographic site plan, cross section, dumping alignment, providing location of benchmark and stake at batches of dumping activity, doing by a river survey team ( including survey manager, hydrographic surveyor, Auto cad operator, etc.) with total station. Sequential stacking of Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks on the engine boat, carrying the Hard rock/ stone/ boulders/C.C blocks/brick blocks/sand cement blocks to dumping area and dumping the block from the boat by manual labour or any other means, all materials & charges etc. complete as per direction of engineer in charge, specification and design.
Volume =
|  | 45x45x45= |  | 257250.6296 |  | x | 0.091125 | = | 23441.9636
|  | 35x35x35= |  | 364501 |  | x | 0.042875 | = | 15627.9804
A) 40-290-10 | Within 200 m. | [7 empty] | 39069.944 | Cum
|  | 30% of = |  |  | = |  | 11720.9832 | Cum | 11720.9832 | Cum
B) 40-280-20 | 200 m to 500 m.
|  | 70 % of = |  |  | = |  | 27348.9608 | cum | 27348.9608 | Cum
7/ 40-320 | Supplying of geo-textile bags (empty) of different sizes and capacity at project/work site, making the bag with standard Geo-Textile fabric (100% Polypropylene Fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, OS<=0.075 mm) and sewing in accordance with the detailed drawing and Technical Specifications included in the Tender Document and Schedule of Rates of BWDB, protecting the geo-textile bags form UV ray or any other damages including cost of all materials, labours, incidental charges etc. complete as per direction of Engineer in charge. .
40-320-15 | Geo-bag; inner size:1100mmx850mm, outer size:1150mmx900mm, geo-fabric th.=>3.0mm, Fill Vol: 0.1333cum; wt: 200kg | Ch. 0.00 to Ch.1.00 at Fulhata Bazar
Chainage km. 0.00 to km. 0.500
|  | Length = |  | 500 | m
|  | 22 |  | per cum
|  | 500 | x | 22 |  | = | 11000 | cum
Chainage km. 0.500 to km. 1.000
|  | Length = |  | 500 | m
|  | 15 |  | per cum
|  | 500 | x | 15 |  | = | 7500 | cum
|  | Total |  |  |  | = | 18500 | Cum
|  | @ 0.1333 cum per bag |  |  |  |  | 0.1333 | Cum
[6 empty] | = | 138784.6962 | Nos | 138785 | Nos
For Guide portion
|  | Area |  | 1000 | 3 |  | 3000 | sqm
Per bag area = 0.75 sqm
|  | No of geo bag = |  |  |  |  | 4000 | Nos
|  | 2 layer |  |  |  |  | 8000 | Nos | 8000 | nos
Chainage km. 0.50 to km. 1.000
For key 2
|  | Area |  | 500 | 3 |  | 1500 | sqm
Per bag area = 0.50 sqm
|  | No of geo bag = |  |  |  |  | 2000 | Nos
|  | 2 layer |  |  |  |  | 4000 | nos | 4000 | nos
|  | Total no of geobag |  |  |  |  | 150785 | Nos
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | Length = |  | 1500 | m
|  | 22 |  | per cum
|  | 1500 | x | 22 |  | = | 33000 | cum
|  | @ 0.1333 cum per bag |  |  |  |  | 0.1333 | Cum
[6 empty] | = | 247561.8905 | Nos | 247562 | nos
For Guide portion
|  | Area |  | 1500 | 3 |  | 4500 | sqm
Per bag area = 0.75 sqm
|  | No of geo bag = |  |  |  |  | 6000 | Nos
|  | 2 layer |  |  |  |  | 12000 | Nos | 12000 | nos
|  | Total no of geobag |  |  |  |  | 259562 | Nos
|  |  |  | Total |  |  | 410347 |  | 410347 | nos
8/ 40-330 | "[Dumping with Barge & Total Station] Filling and dumping of geo-textile bags of different sizes and capacity at project/work site, protecting from UV ray or any other damages, filling with sand (dry and minimum 80% sand must be retained on sieve no 100), sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking with synthetic enamel paint during counting, dumping from properly positioned and anchored flat top barge/pontoon over an area as per drawing, maintaining & recording the dumping position of the barge/pontoon uning total station including loading, unloading, sequential piling of geo-bags on the dumping edge of barge/pontoon, cost of all materials & equipments and its mobilization, labour, incidental charges, etc. complete as per technical specification, approved design and direction of Engineer in charge. [fill volume and weight will be measured after filling with dry sand]"
40-330-15 | Geo-bag; inner size:1100mmx850mm, outer size:1150mmx900mm,, Fill Vol: 0.1333cum; wt: 200kg | Quantity same as geo-bag = |  |  |  |  | 410347 | Nos
9 40-550 | Supplying and laying sand as filter layers as per specific size ranges and gradation including preparation of surface, compacting in layer etc. complete with supply of all materials and as per direction of Engineer in charge.
Chainage km 0.00 to chainage km 0.500
|  | Slope = |  | 5.5902 | m
|  | Top width = |  | 1.2 | m
|  |  |  | 6.7902 | m
Volume =
|  | 540 | x | 6.7902 |  | x | 0.1 | = | 366.6692 | cum
Chainage km. 0.500 to km 1.000
40-550-30 | FM : 1.0 to 1.5 | Slope | = | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Volume =
|  | 520 | x | 9.0262 |  | x | 0.1 | = | 469.3644 | cum
Chainage km 0.500 to km 1.00
|  | Area | = | 500 | 6 | = | 3000 | sqm
Volume =
|  |  |  | 3000 |  | x | 0.15 | = | 450 | cum
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | Slope | = | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Volume =
|  | 1520 | x | 9.0262 |  | x | 0.1 | = | 1371.9882 | cum
[7 empty] | Total |  | 2658.0217 | cum
10 40-520 | Supplying and laying dry 1st class or pick jhama chips as filter in two layers (top and bottom) as per specific size, range and gradation, including breaking chips, grading, preparation of surface, compacting each layer etc. complete with supply of all materials and as per direction of Engineer in charge: | Ch. 0.00 to Ch.1.00 at Fulhata Bazar
Chainage km 0.00 to chainage km 0.500
|  | Slope = |  | 5.5902 | m
|  | Top width = |  | 1.2 | m
|  |  |  | 6.7902 | m
Volume =
|  | 540 | x | 6.7902 |  | x | 0.1 | = | 366.6692 | cum
A)40-520-20 | Well graded between 40mm to 20mm size.
Chainage km. 0.500 to km 1.000
|  | Slope | = | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Volume =
|  | 520 | x | 9.0262 |  | x | 0.1 | = | 469.3644 | cum
Chainage km 0.500 to km 1.00
|  | Area | = | 500 | 6 | = | 3000 | sqm
Volume =
|  |  |  | 3000 |  | x | 0.15 | = | 450 | cum
3 keys
|  | Total no. of Geobag |  |  |  |  | 12000 | Nos
|  | Volume = |  | 1599.6 | cum
[7 empty] | Total |  | 2885.6335 | cum
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | Slope | = | 7.8262 | m
|  | Top width | = | 1.2 | m
9.0262
Volume =
|  | 1520 | x | 9.0262 |  | x | 0.1 | = | 1371.9882 | cum
For Guide portion
|  | 2 layer |  |  |  |  | 12000 | Nos
|  | Volume = |  |  |  |  | 1599.6 | cum
[7 empty] | Total |  | 5857.2217
|  | 50% of | = | 2928.6109 | cum
B)40-520-30 | Well graded between 20mm to 5mm size. (Combination of sub-item 10 & 30 or 20 & 30 shall be used)
|  | same as quantity = |  |  |  |  | 2928.6109 | cum
11 40-500 | Supplying and placing non-woven needle punched type geotextile fabric (100% Polypropylene Fabric, unit weight : 855 Kg/m3 to 946 Kg/m3) as filter materials of elongation at maximum force machine direction (MD) >=60% and <= 100 % , elongation at maximum force (CMD) => 40% and <= 100% ,horizontal and vertical permeability (under 2 kn/m² pressure)=>2x10E-3 m/sec. for effective erosion protection in hydraulic structures/river training works including local handling, placing in position, providing machine seamed joints (with 100% polypropylene or nylon thread) or 35cm lap in dry condition or minimum 100cm lap under water including protecting the geotextile material from UV ray and from any other damages including supply of all materials, labours, equipment’s etc. complete as per direction of Engineer in charge. (Geotextile delivered at site should be certified by ISO and clearly labelled with brand name and grade printed at regular intervals across the body of the fabric).
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
40-500-40 | Mass =>400 gm/m², thickness(Under 2 kpa pressure) =>3.00 mm, EoS<=0.08mm, strip tensile strength =>23 kn/m, grab strength =>1500 N, CBR puncture resistance =>3800 N
Chainage km 0.00 to chainage km 0.500
|  | Slope = |  | 5.5902 | m
Total length
|  | 0.2+0.2+1.2+5.59+0.45+1.35+1= | [8 empty] | 10
[6 empty] | = | 10 | m
|  | Area = |  | 540 |  | x | 10 | = | 5400 | sqm
Lapping
|  | Length = |  | 540
|  | Roll = |  | 4 | m
|  | No of part = |  |  | 135 |  | 135 | Nos
Area =
|  | 135 | x | 10 |  | x | 0.31 | = | 418.5 | sqm
|  | Number of cut piece in one 100 m geo textile | [5 empty] | 10 | 10 | nos
|  | Number of vertical joint |  |  |  | = | 50.3 | 51
Over lapping Vertical
|  | 4 | x | 51 |  | x | 1 | = | 204 | sqm
[7 empty] | Total |  | 6022.5 | sqm
Chainage km. 0.500 to km 1.000
|  | Slope | = | 7.8262 | m | [6 empty] | 20.48
|  | Total length | = | 0.2+0.2+1.2+7.83+0.45+1.35+0.45+6+0.45+1.35+1= |  |  |  |  | m |  | 9.99
|  |  | = | 20.5 | m
|  | Area = |  | 520 |  | x | 20.5
|  | = |  | 10660 | sqm
Lapping
|  | Length = |  | 520
|  | Roll = |  | 4 | m
|  | No of part = |  |  | 130 |  | 130 | Nos
Area =
|  | 130 | x | 20.5 |  | x | 0.31 | = | 826.15 | sqm
|  | Number of cut piece in one 100 m geo textile | [5 empty] | 4.878 | nos
|  | Number of vertical joint |  |  |  |  | 26.65 | 27
Over lapping Vertical
|  | 4 | x | 27 |  | x | 1 | = | 108 | sqm
[8 empty] | Total | 11594.15 | sqm
[6 empty] | Total = |  |  | 17616.65 | sqm
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  | Slope |  | 7.8262
|  | Length |  | 4.5
|  | Total |  | 12.3262
Area
|  | 1520 | x | 12.3262 |  |  | 18735.8816 | sqm
Lapping
|  | Length = |  | 12.3262
|  | Roll = |  | 4 | m
|  | No of part = |  |  | 380 |  | 380 | Nos
Area =
|  | 380 | x | 12.3262 |  | x | 0.31 | = | 1452.0308 | sqm
|  | Number of cut piece in one 100 m geo textile | [5 empty] | 8.1128 |  | nos
|  | Number of vertical joint |  |  |  | = | 46.8397 | 46.8397
Over lapping Vertical
|  | 4 | x | 46.8397 |  | x | 1 | = | 187.3588 | sqm
[7 empty] | Total |  | 20375.2713 | sqm
[7 empty] | Total |  | 37991.9213 | sqm
12 40-920 | Earth work in cutting and filling of eroded bank of river, channel etc. to design slope, including levelling, dressing and compacting the earth in 150mm layers and preparation of the base for bank protection work and use the excess material for filling the ditches on the bank within 50 m or specified in the drawing, if no ditches to be filled then excess material shall be disposed of at least 100 m from the bank line on C/S etc. complete as per direction of Engineer in charge.
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
|  |  |  | Total |  |  |  |  | 3624 | cum
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  |  |  | Total |  |  |  |  | 5436 | cum
|  |  |  | Total |  |  |  |  | 9060 | cum
13 16-130 | Earth work by manual labour in resectioning of embankment/ canal bank/ river slopes/ road/ compound etc. manually compacted by 7.0kg iron rammer to avoid any air pocket in clayey soil (minimum 30% clay, 0-40% silt and 0-30% sand) within the initial lead of 30m and all lifts including throwing the spoils to profile in layers not exceeding 150mm thickness with clod breaking to a maximum size of 100mm, removing roots & stumps of trees of girth upto 200mm from the ground, benching the side slopes, stripping/ ploughing the base of embankment and borrowpit areas, dug bailing, bail out of water, rough dressing including 150mm cambering at the centre of the crest (where necessary) etc. complete as per direction of Engineer in charge.
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
|  |  |  | Total |  |  |  |  | 16400 | cum
Ch. 2.100 to Ch.3.600= 1500m at Sinnikhali
|  |  |  | Total |  |  |  |  | 54600 | cum
A)16-130-10 | 0 m to 3 m height. |  |  | Total |  |  |  |  | 71000 | cum
14 16-720 | Filling ditch/pond/channel/khal etc or land development/improvment by dredged earth from river bed (all kind of soil but excluding organic material) , carried by Bulkhead/cargo/ boat or any other mean, loading and unloading/ Disposing/placing the dredged materials in the designated area upto 1 km from river bank by bulkhead dredger including , maintaining slopes, levelling and dressing in layers upto finished level with all lifts & leads etc. all complete as per direction of the Engineer in charge.
Ch. 0.00 to Ch.1.00 at Fulhata Bazar
|  |  |  | Total |  |  |  |  | 20053.3 | cum
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  |  |  | Total |  |  |  |  | 19984.5 | cum
A)16-720-10 | Bulkhead/cargo/boat or any other means: within 1 km along the river |  |  | Total |  |  |  |  | 40037.8 | cum
15 4-700 | Erection and maintenance of site office and removal of the same after completion of work as per approved plans & drawings for the use of the Engineer-in-charge & his staff, Task force and field laboratory with adequate foundation, brick walls, acceptable outside & inside wall surface, concrete floor with floor tiles, false ceiling of gypsum board, windows are to be glazed & provided with steel grill & screen/blinds, doors with approved locks, furniture & fittings of approved quality, equipment & plant of approved quality, electricity, running water, sewerage, security fencing, 5 KVA stand-bye generator, IBM compatible PC with monitor, uninterruptible power supply (UPS), LaserJet printer (minimum 25 ppm), first aid-box, safety helmet, level/theodolite/EDM, consumables, stationeries, day & night guards & a tea boy and site office shall be ready for occupation by the Engineer-in-charge within 28 days of commencement of work, etc. complete as per direction of Engineer-in-charge. (This is a time related item; proportionate payment for this item shall be made distributing in each bill on the basis of percentage progress of the whole works under contract)
4-700-10 | Site office of minimum 38 sqm plinth area.
|  |  |  | No of site office = |  |  |  |  | 5 | Nos
16 04-710 | Temporary lease of land for 1 (one) year with necessary compensation
Area =
|  | 2 |  | 2500 |  |  | 100 | = | 500000 | sqm
17 10-140 | River Morphological Data Collection/Bathametric and river bank topograpy Survey
|  |  |  | No of section = 25 nos |  |  |  |  | 25 | nos
10-140-40 | 61 m to 100m
18 Market Rate | Pre work, post work and ongoing work Photograp and video of the project work including aerial video and editing.
|  |  |  | No of Video = 25 |  |  | nos |  | 25 | nos
19 28-200 | Reinforced cement concrete work in leanest mix. 1:1.5:3, with 20mm down graded coarse aggregates and sand of FM>2.0 to FM<=2.5, to attain a minimum 28 day cylinder strength of 22.0 N/mm², including breaking, screening, grading, washing aggregates with clean water, mixing, laying in forms, consolidation to levels, curing, including supply of all materials, excluding cost of M.S. work for reinforcements andformworks etc. complete and as per direction of Engineer in charge.
28-200-10 | With stone chips.
For ghat
Cut of wall Top & bot
|  | 4 |  | 0.9 | 4.8 |  | 0.25 | = | 4.32
Base
Top
|  |  |  | 4.8 | 2.5 |  | 0.25 | = | 3
bot
|  |  |  | 4.8 | 2 |  | 0.25 | = | 2.4
Stair
|  |  |  | 10.5 | 3.6 |  | 0.2 | = | 7.56
Step
|  |  |  | 35 | 0.3 |  | 0.15 | = | 0.7875
2
Guide wall
|  | 2 |  | 10.5 | 0.275 |  | 0.2 | = | 1.155
Seat wall
|  | 2 |  | 4.8 | 0.4 |  | 0.25 | = | 0.96
Seat
|  | 2 |  | 4.8 | 0.6 |  | 0.1 | = | 0.576
side
|  | 2 |  | 4.8 | 0.45 |  | 0.225 | = | 0.972
21.7305
|  |  |  | 4 | Nos ghat |  |  | = | 86.922 | Cum
Name plate
Base
|  | 1.45 |  | 0.8 | 0.3 |  | 0.3 | = | 0.1044
Post base to GL
|  | 2 |  | 0.6 | 0.25 |  | 0.25 | = | 0.075
Post above GL
|  | 2 |  | 1.25 | 0.2 |  | 0.2 | = | 0.1
Name plate
|  |  |  | 1.1 | 0.6 |  | 0.2 | = | 0.132
0.4114
|  |  |  | 4 | Nos Name plate |  |  | = | 1.6456 | Cum
[7 empty] | Total = |  | 88.5676 | Cum
20/ 76-110 | M.S. Work for reinforcement with deformed M.S. bar, fy=300 N/mm², (made from billet) in RCC works, including local handling, cutting, forging, bending, cleaning and fabrication with supply of deformed M.S. bar in different sizes and binding with 22 to 18 gages G.I. wire etc. complete including the cost of all materials as per direction of Engineer in charge.
76-110-10 | 8mm dia to 30mm dia.
Cut of wall stair top & bot wall
D-12 @ 150 mm c/c
|  | 4 |  | 2 | 33 |  | 0.9 | 0.89 | 211.464
D-12 @ 150 mm c/c binder
|  | 4 |  | 2 | 7 |  | 4.8 | 0.89 | 239.232
stair D-12 @ 150 mm c/c
[5 empty] | 23 |  | 10.5 | 0.89 | 214.935
[5 empty] | 71 |  | 3.4 | 0.89 | 214.846
6 D-12
|  |  |  | 2 | 6 |  | 10.5 | 0.89 | 112.14
Ring D-10 @ 200 mm c/c
|  |  |  | 2 | 54 |  | 1.9 | 0.62 | 127.224
Seat wall
D-12 @ 200 mm c/c main
|  | 2 |  | 2 | 25 |  | 0.4 | 0.89 | 35.6
D-12 @ 150 mm c/c binder
|  | 2 |  | 2 | 4 |  | 4.8 | 0.89 | 68.352
Seat
3 D-12
|  |  |  | 2 | 3 |  | 0.5 | 0.89 | 2.67
binder
|  |  |  | 2 | 5 |  | 4.8 | 0.89 | 42.72
seat
4 D-12
|  | side |  | 2 | 4 |  | 4.8 | 0.89 | 34.176
D-12 @ 150mm c/c
|  |  |  | 2 | 2 |  | 33 | 0.89 | 117.48
1420.839
|  |  |  | 4 | Nos ghat |  |  | = | 5683.356 | kg
Name plate
base
D-12 @ 150mm c/c
|  |  |  | 2 | 11 |  | 0.8 | 0.89 | 15.664
D-12 @ 150mm c/c binder
|  |  |  | 2 | 6 |  | 1.1 | 0.89 | 11.748
Post
|  | 4D-12 |  | 2 | 4 |  | 1.85 | 0.89 | 13.172
D-10 Ring @ 200
|  |  |  | 2 | 10 |  | 0.8 | 0.62 | 9.92
Plate
7 D-10
|  |  |  | 2 | 7 |  | 0.8 | 0.62 | 6.944
3 D-10
|  |  |  | 2 | 3 |  | 1 | 0.62 | 3.72
61.168
|  |  |  | 4 | Nos Name plate |  |  | = | 244.672 | kg
[7 empty] | Total = |  | 5928.028 | kg
21/ 36-300 | Form work for centering and water tight shuttering as per drawing with wooden planks of different thickness including supply of polythene sheet (1 kg covering 6.5 sqm ) for making shuttering leakproof for all sorts of R.C.C. works in building construction including fitting, fixing by nails, tie rods, nuts and bolts to desired shape and size including levelling and removing the forms etc. after specified period including the cost of all materials as per direction of Engineer in charge.
36-300-10 | Individual and continuous footing of column, raft etc. with 25mm thick wooden planks.
Cut of wall
|  |  |  | 2 | 4 |  | 0.9 | 4.8 | 34.56
seat bot base
[5 empty] | 2 |  | 4.8 | 0.25 | 2.4
|  | side |  |  | 2 |  | 2.5 | 0.25 | 1.25
|  | stair |  |  | 2 |  | 10.5 | 0.2 | 4.2
|  | side |  |  | 2 |  | 3.6 | 0.2 | 1.44
|  | step |  |  | 35 |  | 0.15 | 3.6 | 18.9
Guide wall
[5 empty] | 2 |  | 10.5 | 0.2 | 4.2
[5 empty] | 2 |  | 10.5 | 0.15 | 3.15
Seat wall
|  |  |  | 2 | 2 |  | 4.8 | 0.4 | 7.68
|  | face |  | 2 | 2 |  | 0.4 | 0.25 | 0.4
|  | Seat bot |  |  | 2 |  | 0.5 | 4.8 | 4.8
|  | side |  | 2 | 2 |  | 0.5 | 0.2 | 0.4
|  | face |  |  | 2 |  | 4.8 | 0.2 | 1.92
85.3
|  |  |  | 4 | Nos ghat |  |  | = | 341.2 | sqm
Name plate
|  | base |  |  | 2 |  | 1.45 | 0.375 | 1.0875
|  | side |  |  | 2 |  | 0.8 | 0.375 | 0.6
|  | column |  |  | 2 |  | 1.85 | 1 | 3.7
|  | plate |  |  | 2 |  | 0.6 | 1.1 | 1.32
|  | bot |  |  | 2 |  | 0.6 | 0.2 | 0.24
[9 empty] | 6.9475 | sqm
|  |  |  | 4 | Nos Name plate |  |  | = | 27.79 | sqm
[7 empty] | Total | = | 368.99 | sqm
22/ 40-460 | [Geo-textile bag filled with sand cement mixture] Supplying filling and placing of geo-textile bags of different sizes and capacity at project/work site, making with standard geo-textile fabric (100% Polypropylene fabric, mass>= 400gm/m², unit weight : 855 Kg/m3 to 946 Kg/m3, EOS<=0.075 mm) and sewing in accordance with the drawing and Technical Specifications of BWDB and Schedule of Rates of BWDB, filling with sand-cement mixed (6:1 Proportion, sand: F.M ≥ 1.00, Portland cement) , sewing along one transverse (top) side after filling, staking in measurable/countable stakes, marking by synthetic enamel paint during counting, placing in position as per approved drawing including levelling, dressing and preparation of base, cost of all materials & equipments and its mobilization, labour, incidental charges etc. complete as per technical specification, approved design and direction of Engineer in charge.
40-460-10 | Geo-bag; inner size:950mmx750mm, outer size:1000mmx800mm geo-fabric th.=>3.0mm, Fill Vol: 0.0840cum; wt: 125kg
Detail
|  | Area |  | 2580 |  | x | 3 | = | 7740 | sqm
Par bag area = 0.50 sqm
|  | No of geo bag = | [6 empty] | 15480 |  |  | 1590
|  | 2 layer = | [6 empty] | 30960 | Nos
23 | Earth work in excavation of foundation trenches in all kinds of soils including levelling, dressing, placing, removal of spoils to a safe distance with initial lead of 30m and lift of 1.5m as per direction of Engineer in charge. | Ch. 0.00 to Ch.1.00 at Fulhata Bazar
16-500 |  |  |  | Total |  |  |  |  | 1577.5 | cum
Ch. 2.600 to Ch.4.100= 1500m at Sinnikhali
|  |  |  | Total |  |  |  |  | 1511.25 | cum
|  |  |  | Total |  |  |  |  | 3088.75 | cum
24 28-120 | Cement concrete work in leanest mix. 1:3:6 with sand of FM>=1.5, in foundation or floor including breaking, screening, grading and washing aggregates with clear water, mixing, laying in position, consolidation to levels, curing, including supply of all materials, excluding the cost of formworks etc. complete as per direction of Engineer in charge.
28-120-20 | With 25mm down graded stone chips. | 2580 |  | 0.5 | 0.2 |  | 0.15 | = | 38.7 | cum
(Muhammad Abu Hanif)
Sub-Asstt. Engineer/SO
Jhalodanga O&M Section
BWDB, Bagerhat.
(Faruk Ahmed)
Sub-Divisional Engineer
Bagerhat O&M Sub-Division
BWDB, Bagerhat.