## Resource_List
Code | Name | Unit | DC101 | DF101 | DF102 | DF103
501 | AE,Sakib | hr | 0.5 | 0 | 0 | 0
601 | DFM,Harris | hr | 0 | 0.5 | 0.5 | 0
602 | DFM,Harris | hr | 0 | 0 | 0 | 0
603 | DFM,Mousumi | hr | 0 | 0 | 0 | 0.5

## Resources_Consumption
Code | Name | Unit | DC101 | DF101 | DF102 | DF103 | DC102
401 | AE,Sakib | hr | 1 | 0 | 0 | 0 | 1
501 | DFM,Harris | hr | 0 | 1 | 1 | 0 | 0
503 | DFM,Mousumi | hr | 0 | 0 | 0 | 1 | 0

## WBS3
TaskNo | Name | Duration | Predecessor | order
0 | Contract | 0 | 4,5
1 | Mobilization and Site Preparation | 7 | 3,4 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 5 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 2 | 6
4 | Embankment Construction | 34 | -1 | 2
5 | Placing Sand Filter | 10 | -1 | 3

## WBS
TaskNo | Name | Duration | Predecessor | order
1 | Mobilization and Site Preparation | 7 | -1 | 1
2 | CC Block Manufacture(30X30X30) | 16 | 1 | 7
3 | CC Block Manufacture(40X40X20) | 16 | 1 | 6
4 | Embankment Construction | 34 | 1 | 2
5 | Placing Sand Filter | 10 | 4 | 3
6 | Placing Geotextile Filter | 10 | 5 | 4
7 | Placing Pea Gravel Filter | 10 | 6 | 5
8 | Placing CC Block | 10 | 2,3,7 | 8
9 | Ancilary Work for Site Completion | 7 | 8 | 9

## Main
Name | Start | Finish | Allocation_Sheet_Name | Site Name
Steel_Compression_Member | 1 | 7 | Steel_Compression_Member | Steel Structure: Compression Member

## Steel_Compression_Member
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Void | 3 | -1 | Percent | 100 | DC101
2 | Compression Member Part_1_2 | 1 | 1 | Percent | 100 | DC102
3 | Compression Member Part_3_4 | 1 | 2 | Percent | 100 | DF101
4 | Compression Member Part_5 | 1 | 3 | Percent | 100 | DF101
5 | Group Discussion and Problem Solving | 1 | 4 | Percent | 100 | DF102

## T_A_35M_M1210_TO_M1245
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1190 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 2866 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 462 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 49 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 546 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 55 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 4056 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_37M_M8760_TO_M8797
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 2 | 1 | Nos | 1258 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 5 | 1 | Nos | 3030 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 7 | 1 | Cum | 489 | 16-240
6 | Placing Sand Filter | 4 | 4,5 | Cum | 52 | 40-550-10
7 | Placing Geotextile Filter | 4 | 4,5 | sqm | 577 | 40-500-40
8 | Placing Pea Gravel Filter | 4 | 4,5 | Cum | 58 | 40-530-30
9 | Placing CC Block | 4 | 4,5 | Nos | 4288 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_200M_M10100_TO_M10300
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 13 | 1 | Nos | 6800 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 13 | 1 | Nos | 16376 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 2640 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 276 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 3118 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 312 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 23176 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_110M_M12330_TO_M12440
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 3740 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 9007 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 30 | 1 | Cum | 4172 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 438 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 4927 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 494 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 12747 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_72M_M12712_TO_M12784
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 4 | 1 | Nos | 2448 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 10 | 1 | Nos | 5896 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 951 | 16-240
6 | Placing Sand Filter | 6 | 4,5 | Cum | 100 | 40-550-10
7 | Placing Geotextile Filter | 6 | 4,5 | sqm | 1123 | 40-500-40
8 | Placing Pea Gravel Filter | 6 | 4,5 | Cum | 113 | 40-530-30
9 | Placing CC Block | 6 | 4,5 | Nos | 8344 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_133M_M21600_TO_M21733
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 7 | 1 | Nos | 4522 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 17 | 1 | Nos | 10890 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 21 | 1 | Cum | 1756 | 16-240
6 | Placing Sand Filter | 12 | 4,5 | Cum | 184 | 40-550-10
7 | Placing Geotextile Filter | 12 | 4,5 | sqm | 2074 | 40-500-40
8 | Placing Pea Gravel Filter | 12 | 4,5 | Cum | 208 | 40-530-30
9 | Placing CC Block | 12 | 4,5 | Nos | 15412 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_105M_M22375_TO_M22480
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 5 | 1 | Nos | 3570 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 8598 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 21 | 1 | Cum | 1386 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 145 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 1637 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 164 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 12168 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_100M_M25170_TO_M525270
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 14 | 1 | Nos | 3400 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 14 | 1 | Nos | 8188 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 30 | 1 | Cum | 1320 | 16-240
6 | Placing Sand Filter | 10 | 4,5 | Cum | 138 | 40-550-10
7 | Placing Geotextile Filter | 10 | 4,5 | sqm | 1559 | 40-500-40
8 | Placing Pea Gravel Filter | 10 | 4,5 | Cum | 156 | 40-530-30
9 | Placing CC Block | 10 | 4,5 | Nos | 11588 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_180M_M25720_TO_M25900
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 9 | 1 | Nos | 6120 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 24 | 1 | Nos | 14739 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 40 | 1 | Cum | 5413 | 16-240
6 | Placing Sand Filter | 17 | 4,5 | Cum | 567 | 40-550-10
7 | Placing Geotextile Filter | 17 | 4,5 | sqm | 6393 | 40-500-40
8 | Placing Pea Gravel Filter | 17 | 4,5 | Cum | 641 | 40-530-30
9 | Placing CC Block | 17 | 4,5 | Nos | 20859 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_A_78M_M25925_TO_M26003
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | Percent | 100 | NS101
2 | CC Block Manufacture(30X30X30) | 4 | 1 | Nos | 2652 | 40-190-50
3 | CC Block Manufacture(40X40X20) | 10 | 1 | Nos | 6387 | 40-190-40
4 | Curing CC Block | 21 | 2,3 | Percent | 100 | NS105
5 | Embankment Construction | 15 | 1 | Cum | 1030 | 16-240
6 | Placing Sand Filter | 6 | 4,5 | Cum | 108 | 40-550-10
7 | Placing Geotextile Filter | 6 | 4,5 | sqm | 1217 | 40-500-40
8 | Placing Pea Gravel Filter | 6 | 4,5 | Cum | 122 | 40-530-30
9 | Placing CC Block | 6 | 4,5 | Nos | 9039 | NS106
10 | Ancilary Work for Site Completion | 7 | 9 | Percent | 100 | NS102

## T_B5_425M_M9175_TO_M9600
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 6197 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 6881 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 5861 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_167M_M9785_TO_M9952
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2436 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 2704 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 2303 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_100M_M10300_TO_M10400
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 1458 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 1619 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 1379 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_255M_M12075_TO_M12330
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 3718 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 4129 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 3517 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## T_B5_150M_M24950_TO_M25100
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | Embankment Construction | 15 | 1 | Cum | 2187 | 16-240
3 | Placing Geotextile Filter | 7 | 2 | sqm | 2429 | 40-500-40
4 | Close Turfing | 7 | 2 | Nos | 2069 | 48-100
5 | Ancilary Work for Site Completion | 7 | 4 | Percent | 100 | NS102

## FF_15M_5560M
TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
1 | Mobilization and Site Preparation | 7 | -1 | percent | 100 | NS101
2 | CC Block Manufacture(50X50X50) | 9 | 1 | Nos | 1798 | 40-190-15
3 | CC Block Manufacture(50X50X30) | 11 | 1 | Nos | 7312 | 40-190-05
4 | CC Block Manufacture(40X40X40) | 6 | 1 | Nos | 1781 | 40-190-35
5 | CC Block Manufacture(40X40X20) | 7 | 1 | Nos | 3917 | 40-190-40
6 | Curing | 21 | 2,3,4,5 | percent | 100 | NS105
7 | Ring Bundh construction | 5 | 1 | Cum | 2052 | 40-450
8 | Excavation | 4 | 1 | Cum | 1598 | 16-510
9 | Embankment Construction | 15 | 7 | Cum | 4479 | 16-240
10 | Placing Sand Filter | 9 | 9 | Cum | 460 | 40-550-10
11 | Placing Geotextile Filter | 9 | 9 | sqm | 3117 | 40-500-40
12 | Placing Pea Gravel Filter | 9 | 9 | Cum | 613 | 40-530-30
13 | Geo Bag Placing(175) Kg | 9 | 9 | Nos | 4047 | 40-380-20
14 | Placing CC Block | 9 | 9 | Nos | 14808 | NS106
15 | Ring Bundh Removal | 5 | 14 | percent | 1641 | 16-470
16 | Ancilary Work for Site Completion | 7 | 15 | Percent | 100 | NS102

## Equipment Production Rate
CC Bock | L | B | H | Relative Size wrt 30X30X30 | Standard Production Rate | Block/machine |  | code
50X50X50 | 50 | 50 | 50 | 4.6296 | 750 | 162 | 0.0061728 | 40-190-15
50X50X30 | 50 | 50 | 30 | 2.7778 | 750 | 270 | 0.0037037 | 40-190-05
40X40X40 | 40 | 40 | 40 | 2.3704 | 750 | 317 | 0.0031546 | 40-190-35
40X40X20 | 40 | 40 | 20 | 1.1852 | 750 | 633 | 0.0015798 | 40-190-40
30X30X30 | 30 | 30 | 30 | 1 | 750 | 750 | 0.0013333 | 40-190-50
|  |  |  | Equipment |  | Daily Prod(8hrs)
|  |  |  | Excavator |  | 300
|  |  |  | Roller |  | 760 | 0.0013158
|  |  |  | Mixuture Machie |  | 17
CC Block Placing
Block Size | L | B | H | Realtive Area | Standard Prod/Day | Daily Production
50X50X30 | 50 | 50 | 30 | 1.5625 | 1400 | 896
50X50X20 | 50 | 50 | 30 | 1.5625 | 1400 | 896
40X40X40 | 40 | 40 | 40 | 1 | 1400 | 1400
40X40X20 | 40 | 40 | 20 | 1 | 1400 | 1400
30X30X30 | 30 | 30 | 30 | 0.5625 | 1400 | 2489
175 kg geobag |  |  |  | 245/day by group 20 incld bed prep

## Block Placing Production Rate
1 Group | 20 Labour
Dayliy Placing Including Bed Preparation for 40X40X20 CC Block | 1400 | Nos
unit area of block | 0.16 | sqm
Bed Area | 224 | sqm
Sand Filter 100mm thick | 22.4 | cum
Geo Textile Filter | 224 | sqm
Gravel Filter | 22.4 | cum

## Project_name
Name
Submersible Embankment Slope Protection Work at Kishoregonj PW-34