## Steel_Compression_Member
| TaskNo | Name | Duration | Predecessor | Unit | Volume | TaskCode
0 | 1 | Void | 3 | -1 | Percent | 100 | DC101
1 | 2 | Compression Member Part_1_2 | 1 | 1 | Percent | 100 | DC102
2 | 3 | Compression Member Part_3_4 | 1 | 2 | Percent | 100 | DF101
3 | 4 | Compression Member Part_5 | 1 | 3 | Percent | 100 | DF101
4 | 5 | Group Discussion and Problem Solving | 1 | 4 | Percent | 100 | DF102

## Steel_Compression_Member-mat
| TaskNo | Task_Name | Start Day | Finish Day | Durations | Unit | H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11 | H12 | H13 | H14 | H15 | H16 | H17 | H18 | H19 | H20 | H21 | H22 | H23 | H24 | H25 | H26 | H27 | H28 | H29 | H30 | H31 | Task Vol | Work_rate
0 | 1 | Void | 1 | 3 | 3 | Percent | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 34
1 | 2 | Compression Member Part_1_2 | 4 | 4 | 1 | Percent | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
2 | 3 | Compression Member Part_3_4 | 5 | 5 | 1 | Percent | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
3 | 4 | Compression Member Part_5 | 6 | 6 | 1 | Percent | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
4 | 5 | Group Discussion and Problem Solving | 7 | 7 | 1 | Percent | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100